SCHEDULE 1 — STATEMENT OF WORK (SOW-01)

to the Master Services Agreement dated 14 March 2024

## 1.  Scope

1.1  The Supplier shall deliver the Platform in two phases: Phase 1 (core inventory and EPOS); Phase 2 (reporting and analytics). The agreed scope does not include a customer loyalty module.

## 2.  Implementation timetable

| Milestone | Description | Target date |
| --- | --- | --- |
| M1 | Design sign-off | 30 April 2024 |
| M2 | Build complete (Phase 1) | 31 July 2024 |
| M3 | User acceptance testing | 13 September 2024 |
| M4 | Go-live (target date) | 1 October 2024 |

2.1  The go-live date of 1 October 2024 is a target date. The detailed implementation plan is a planning estimate and is subject to the change control procedure in clause 3 of the MSA.

## 3.  Responsibilities of the Customer

3.1  The Customer shall provide timely access to data, systems, and personnel, and shall procure and maintain adequate in-store network connectivity.

3.2  Training of the Customer’s store and head-office staff in the use of the Platform is the responsibility of the Customer. The Supplier shall provide a train-the-trainer session and written user guides only.

## 4.  Payment milestones

4.1  Charges are payable 25% on each of M1, M2, M3 and M4, subject to any variation agreed under the change control procedure.