EMAIL CORRESPONDENCE

Thread: New requirement — loyalty module

| From: | Helena Vance <h.vance@meridianretail.co.uk> |
| --- | --- |
| To: | Marcus Reilly <m.reilly@techflow-solutions.co.uk> |
| Cc: | Priya Nair <p.nair@meridianretail.co.uk> |
| Sent: | 21 August 2024 09:14 |
| Subject: | New requirement — customer loyalty module |

Marcus,

Following the marketing review, the board wants a customer loyalty capability included in the platform before we go live — points accrual, redemption at the till, and a member database. I appreciate this was not in the original SOW, but it is now a priority for us.

Can you scope this as a change and let us have the cost and any timetable impact? We accept there may be a knock-on to the go-live date and we are willing to discuss a revised date to accommodate it.

Helena

| From: | Marcus Reilly <m.reilly@techflow-solutions.co.uk> |
| --- | --- |
| To: | Helena Vance <h.vance@meridianretail.co.uk> |
| Cc: | Priya Nair <p.nair@meridianretail.co.uk> |
| Sent: | 27 August 2024 15:39 |
| Subject: | RE: New requirement — customer loyalty module |

Helena,

Thanks. We’ve scoped the loyalty module. The additional cost is £180,000 and, given the additional build and test, we will need to move go-live from 1 October to 18 November 2024. I’ll issue Change Order 3 for Priya’s signature to confirm both the scope and the revised date.

Marcus